## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create login/logout system | 1 | 4 | 8 | 1 | 100%
Create delete account function | 2 | 4 | 8 | 1 | 100%
Create to-do list | 4 | 4 | 8 | 1 | 100%
Create feature that allows Users to make their own flashcards | 4 | 4 | 8 | 1 | 100%
Render templates for flashcards | 4 | 4 | 8 | 1 | 100%
Search Flash cards | 5 | 4 | 8 | 1 | 100%
Study tracker | 5 | 4 | 8 | 1 | 100%
Markdown notes | 8 | 4 | 9 | 2 | 0%
Option to Share Flash cards | 6 | 4 | 8 | 2 | 100%
Markdown to pdf | 6 | 4 | 8 | 2 | 100%
Visualize Time Blocks | 8 | 4 | 8 | 2 | 0%
Pomodoro timer | 9 | 4 | 8 | 2 | 100%
Order flash cards | 8 | 4 | 8 | 2 | 0%
Ability to navigate between notes | 8 | 4 | 9 | 2 | 0%
Markdown to HTML | 8 | 4 | 8 | 2 | 100%
Track hours worked | 8 | 4 | 8 | 2 | 10%
Flash cards to PDF | 8 | 4 | 9 | 2 | 0%